## Project Timeline
PROJECT TIMELINE TEMPLATE
PROJECT TITLE |  | Pandas STock Analysis
PROJECT TEAM |  | Tracie B, Ariana F, Luan Ng, James Y, Brandon J
PHASE |  |  | DETAILS | P.I.C | Status
PROJECT WORKING DAY:
DAY 1 & 2 | Project Conception and Initiation |  | - Project PROPPOSAL | all team | COMPLETED | PRESENT DAY
|  |  | - Github Repo | Tracie
|  |  | - searching data sets | all team
|  |  | - Buy a domain for web | Tracie
|  |  | - agreed on data sets | all team
DAY 3 | Project detail Planning & Starting steps |  | - manipulating data | James ¦ Tracie | completed
|  |  | - HTML ¦ CSS draft | Tracie | completed
|  |  | - HTML ¦ CSS develop more | Luan | completed
|  |  | - Web direction ¦ checklist | Tracie | completed
|  |  | - SQL database | Tracie | on-going
DAY 4 | Deeper diving |  | - Plotting Pharma | James
|  |  | - Plotting Tech | Brandon
|  |  | - Plotting Finance | Tracie
|  |  | - Flask ¦ APi | Luan
DAY 5 | Fine-tune the web for presentation |  | - Plotting to be finished | all team
|  |  | - Link all plot.js to html & css | James
|  |  | - HTML ¦ CSS develop to pretty layout per direction | Ariana
|  |  | - Push all into domain | Brandon
FINAL DAY | G-TIME: PRESENTATION |  | - Home page
- Data source page
- Industry 3 pages